## ProjectSchedule
Customer Notification System
The Architects |  | Project Start: | 2023-09-05
|  | Project End: | 2023-12-11
|  | Display Week: | 1 |  |  | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23
 | time axis 2023-09-04 to 2023-10-29
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-09-04 to 2023-10-29
Phase 1: Packaging, Testing, and Research
Create Basic Hello World Installer | Gavin | 100% | 2023-09-05 | 2023-09-07 | 3
Create Javascript Hello World Installer | Gavin | 100% | 2023-09-12 | 2023-09-14
Create first Iteration of Server Installer | Gavin | 100% | 2023-09-15 | 2023-09-21 | 7
Fully Operational Version of Server Installer | Gavin & Faisal | 70% | 2023-09-22 | 2023-10-18
Researching Deployment Options | Henry & Usama | 100% | 2023-09-22 | 2023-10-04
Sign up for Server | Usama | 100% | 2023-10-05 | 2023-10-10
Phase 2: Adding Test Cases and Getting Server Ready
Getting RTL Setup | Andres | 100% | 2023-09-22 | 2023-09-27 | 6
Adding Test Cases to Server Files | Andres & Faisal | 75% | 2023-09-28 | 2023-10-19
Adding Test Cases to Client Files | Andres & Henry | 50% | 2023-09-28 | 2023-10-19 | 22
Sign up for Server | Usama | 100% | 2023-10-05 | 2023-10-08
Register Domain | Usama | 100% | 2023-10-08 | 2023-10-10
Phase 3: Preparatory Launch and
Insert new rows ABOVE this one
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.